## Initiating
Checklist #1 – The Initiating Phase
Capture the objective of the project in 1 complete, succinct sentence
High-level project schedule milestones identified
High-level scope of work identified
High-level project resources (budget and people) identified
1st Draft of the Stakeholder Management Tool Developed
Complete the Project Charter (if needed)
Hold the project kick-off meeting

## Planning
Checklist #2 – The Planning Phase
Regular team meetings scheduled for the expected duration of the project
The Communication Plan has been completed
Project lifecycle model has been identified
Project requirements are frozen and formal change control is now in effect
Change Control Board established
The release readiness checklist has been developed
The risk register has been developed and the top risks have active risk management plans identified
All stakeholders agree to the project timeline milestones
Schedule has been baselined

## Executing
Checklist #3 – The Execution Phase
Standing team meetings are effective and held regularly with a stated agenda
Changes to the Plan of Record are managed effectively through the project and program level CCBs
The project schedule is updated regularly, incorporating unplanned work as needed
Project execution metrics have been established, are monitored regularly, and drive corrective actions as needed
Project risks are reviewed regularly with new risks identified and action plans updated as needed
Project status updates are provided to key stakeholders on a regular cadence
Problems impeding the team’s ability to execute the project plan are efficiently escalated

## Releasing
Checklist #4 – Releasing the Project Deliverables
Ensure all items on the Release Readiness Checklist have been completed
For Release Readiness Checklist items that cannot be completed prior to the release, obtain the necessary waivers and stakeholder approval, prior to the release
Complete the release plan (all work identified and organized into a logical flow, event scheduled, communication plan ready)
Release approval/”Go/No Go” decision criteria confirmed with key stakeholders
Release activity completed
Formal release approval obtained
Formal notification of release status provided to key stakeholders

## Closing
Checklist #5 – Closing the Project
Facilitate the Project Retrospective
Clean House
All project material (HW & SW) appropriately dispositioned
All collateral posted to their permanent locations
Important project artifacts archived
Project summary published
All key stakeholders agree that the project work is complete
Hold a celebration for the team (if warranted)
Recognize individual team members for their contributions (if warranted)
Resources released from the project and available for other work